## Sheet1
DATE	SUMMARY	TO-DO	Attended	Length	Links & Docs
30/09/2022	First meeting with the team. Discussed the list of projects and shortlisted our top 10 choices. We also procured our more desirable top 3 that we would like to bid for.	Start drafting CVs	07/07	01:30:00	Shortlist
06/10/22	We attended the lab to discuss the allocation of EOI documents for the projects we have chosen. We chose Alfie to do Smart Receipts, Vishal to do Find AR, and Olly to do Stock Exchange. This will likely change as we understand more on what work needs to be done from the 10/06/22 lecture on EOI.	Draft out the EOI documents for the meeting on 12/10/22. Each team member to list out their applicable skills for each project.	07/07	01:00:00
07/10/22	We attended the team workshop, and learnt better teamwork and communication skills.		07/07	02:00:00
11/10/22	We reassigned the EOIs to subteams and are to be done in the week. Each subteam will assign a team member to write up a certain part of the EOI, such as analysis or motivation.	Draft the EOI documents for this week, preferably by thursday	07/07	00:45:00
12/10/22	We confirmed what each subteam has created for their EOIs, and then worked on connecting the separated eoi parts together to form a cohesive document for each project. This was partially completed in the 2 hours.	Finish the EOI document for the next meeting	07/07	02:00:00
14/10/22	We peer-reviewed the finished EOIs of each sub-team, fixing any grammar mistakes and accepting ideas from the whole team to reach an agreed upon eoi. We then confirmed that each subteam will create slides and a rough script to follow for the pitches.	Create pitch slides and script by Sunday.	06/07, Oliver missing	01:00:00
17/10/2022	We analysed the progress of each subteam. The script for Smart Receipts was completed, slides nearly done. Script for Find AR was in progress to be put together, and the slides were done. Slides for Stocks were mostly done in the meeting, and the script was in need of some work. We deemed it possible to finish the material on sunday, and record the videos on monday.	Finish Pitch slides and scripts by Sunday. Record Pitch Videos on Monday afternoon	06/07, Alex Missing due to Parol Service	01:30:00
27/10/2022	We created some general user stories with a trello board, more of the form of epics/themes to be split up later. We also created personal trello boards for IBM skills.	Finish splitting user stories to a doable form for 2/11/2022 in our meeting with IBM	06/07, Oliver missing	02:00:00