## Sheet1
DATE	SUMMARY	TO-DO	Attended	Length	Links & Docs
30/09/2022	First meeting with the team. Discussed the list of projects and shortlisted our top 10 choices. We also procured our more desirable top 3 that we would like to bid for.	Start drafting CVs	07/07	01:30:00	Shortlist
06/10/22	We attended the lab to discuss the allocation of EOI documents for the projects we have chosen. We chose Alfie to do Smart Receipts, Vishal to do Find AR, and Olly to do Stock Exchange. This will likely change as we understand more on what work needs to be done from the 10/06/22 lecture on EOI.	Draft out the EOI documents for the meeting on 12/10/22. Each team member to list out their applicable skills for each project.	07/07	01:00:00
07/10/22	We attended the team workshop, and learnt better teamwork and communication skills.		07/07	02:00:00
11/10/22	We reassigned the EOIs to subteams and are to be done in the week. Each subteam will assign a team member to write up a certain part of the EOI, such as analysis or motivation.	Draft the EOI documents for this week, preferably by thursday	07/07	00:45:00
12/10/22	We confirmed what each subteam has created for their EOIs, and then worked on connecting the separated eoi parts together to form a cohesive document for each project. This was partially completed in the 2 hours.	Finish the EOI document for the next meeting	07/07	02:00:00
14/10/22	We peer-reviewed the finished EOIs of each sub-team, fixing any grammar mistakes and accepting ideas from the whole team to reach an agreed upon eoi. We then confirmed that each subteam will create slides and a rough script to follow for the pitches.	Create pitch slides and script by Sunday.	06/07, Oliver missing	01:00:00
17/10/2022	We analysed the progress of each subteam. The script for Smart Receipts was completed, slides nearly done. Script for Find AR was in progress to be put together, and the slides were done. Slides for Stocks were mostly done in the meeting, and the script was in need of some work. We deemed it possible to finish the material on sunday, and record the videos on monday.	Finish Pitch slides and scripts by Sunday. Record Pitch Videos on Monday afternoon	06/07, Alex Missing due to Parol Service	01:30:00
27/10/2022	We created some general user stories with a trello board, more of the form of epics/themes to be split up later. We also created personal trello boards for IBM skills.	Finish splitting user stories to a doable form for 2/11/2022 in our meeting with IBM	06/07, Oliver missing	02:00:00
01/11/2022	We created the story maps for each of our three themes. These story maps split up our initial large user stories (themes) into epics and their user stories that can be done in a 2 week sprint.	Finish the "Manage tags" Story Map	04/07, Oliver, Alex, Aidan missing. Aidan stated he wouldn't make it.	01:45:00
02/11/2022	We had a meeting with our industry sponsor to clear some confusion on project requirements. We discussed using IBM services, and found some differences in our interpretation.	Edit Story maps, and create a MoSCoW analysis list.	07/07	00:30:00
09/11/2022	This meeting had the primary goal of assigning sub teams and beginning a sprint. We also discussed how to approach the interim report, and that everyone was clear on our user stories and the general plan. We decided to do a half-sprint to set-up the basic website, database, and research/design an AR solution.	Finish Trello user story assignments, and add research/findings/testing to Interim Draft in git.	07/07	01:00:00
17/11/2022	This was the retrospective of Sprint 1. We went over what everyone achieved, and edited out user-story composition to better outline what we know now. Through this, we assigned the next user stories to do to each sub-team and made sure everyone knew what to do.	Finish Sprint 2.	07/07	00:45:00
18/11/2022	Vishal catched up with our client over what we have achieved. He was content with our progress, that being the complete formulation of user stories and what we envision the website to be.		01/01	00:15:00
30/11/2022	This was the retrospective of Sprint 2. We went over the issues we had on this sprint, the main issue being the Server hosting issue due to lacking permissions. We then assigned the Interim report in pieces to everyone, and reassigned the incomplete user stories for a 1 week + 2 day sprint.	Finish Sprint 3.	04/07, Oliver, Alex missing. Vishal stated he wouldn't make it.	00:30:00
11/12/2022	This was a retrospective of Sprint 3. Moreso, it reiterated the point to get the interim report done, and to make sure everyone knows what they were assigned.	Finish Interim Report	06/07, Vishal missing.	00:40:00
31/01/2023	This was a meeting for assignign user stories for Sprint 4, and figuring out and confirming development methods due to IBM's lack of software support. We decided to continue with the Severless Methodology, and Alfie confirmed that everyone understood how to setup a local instance of the server to start development. We then assigned user stories to three teams, for a 1 week sprint.	Finish Sprint 4	07/07	01:30:00
01/02/2023	We had a meeting with the supervisor about IBM and software troubles in accessing vital systems for development.	Contact IBM to see if issue can be rectified	04/07, non-mandatory	00:15:00
07/02/2023	We had a retrospective on our 4th sprint, and from this we assigned new user stories to teams, and rehashed the teams a bit for more specific arrangements dependening on the teams specialities. We will change this around next sprint to allow knowledge distribution. Most of the user stories were finished from the previous sprint, so good progress was made.	Finish Sprint 5	07/07	00:45:00
14/02/2023	We had a retrospective on our 5th sprint, and assigned new user stories for the teams. Alfie also explained how the backend works by showing the User login and creation API for preparations of moving the teams around to spread knowledge evenly, and will change the teams next sprint as some of the current user stories need still need completing	Finish Sprint 6	06/07, Aidan stated he wouldn't be able to make it	01:00:00
22/02/2023	Vishal had a meeting with the client to discuss progress. The client requested videos and photos depicting how the system works.		01/07	00:15:00
21/02/2023	We had a meeting with Geert, and then our 6th sprint retrospective. We did not complete as much as we hoped, so a lot of the previous user stories were re-assigned.	Finish Sprint 7	06/07, Vishal stated he wouldn't be able to make it due to illness	01:30:00
28/02/2023	Our 7th retrospective was done, and some substantial work was done in the backend and frontend.	Finish Sprint 8	06/07, Olly was absent	00:45:00
01/03/2023	Meeting with supervisor going over progress, and how to incoporate user studies and better justification in design choices.		02/07, Alfie and Vishal	00:25:00
07/03/2023	Our 8th Retrospective was done, finishing the backend and putting much more focus getting the user experience complete on the frontend.	Finish Sprint 9	06/07, Olly was absent	01:00:00